## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | Profiles
1.1 | As an unregistered user, I should be able to create an account as a member, a partner, a consultancy agency, an educational organisation, or a partner coworking space (so that I can begin to use LirtenHub). | 1 | Mariam El-Shrif | Shamel Khalil | Ahmed Ashraf
1.2 | As a consultancy agency or partner, I should receive a notification containing an appointment to sign contracts and agreements with LirtenHub (so that I can begin working with LirtenHub). | 1 | Bishoy | Mikkawy | Mostafa
1.3 | As a member, I should be required/able to fill in or update my personal information, events attended, projects/tasks/jobs completed, and the masterclasses/certificates held on my profile (so that LirtenHub can begin to recommend tasks/jobs to me that suit my profile). | 1 | Ebraam | Mariam El-Shrif | Bishoy
1.4 | As a consultancy agency, I should be required/able to fill in or update my business information, partners, board members, and events organised (so that members can learn more about my agency). | 1 | Mariam El-Shrif | Shamel Khalil | Ahmed Ashraf
1.5 | As a partner, I should be able to leave a review on a member’s profile after I’ve worked with them (so that future partners working with this member can see how they’ve done previously). | 2 | Shamel Khalil | Mariam El-Shrif | Ahmed Ashraf
1.6 | As a partner, I should be able to fill in or update my business information, partners, board members, events organised, and field of work (so that other users can view my information). | 1 | Bishoy | Mostafa | Mikkawy
1.7 | As a partner, I should have my previous completed projects automatically listed on my profile (so that users can view older projects). | 3 | Mostafa | Mikkawy | Bishoy
1.8 | As a member, I should be able to complete a form to give feedback on a partner that I’ve worked with before by visiting their profile (so that future members can see how they’ve done previously). | 2 | Mikkawy | Mostafa | Bishoy
| As a member, I should have masterclasses I’ve completed automatically listed on my profile (so that visitors of my page may view them). | 3 | Ahmed Ashraf | Mariam El-Shrif | Shamel Khalil