## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | As an unregistered user, I should be able to create an account as a member, a partner, a consultancy agency, an educational organisation, or a partner coworking space (so that I can begin to use LirtenHub). | 1 | Bishoy | Mostafa | Ahmed Ashraf
2 | As a consultancy agency or partner, I should receive a notification containing an appointment to sign contracts and agreements with LirtenHub (so that I can begin working with LirtenHub). | 1 | Bishoy | Mikkawy | Mostafa
3 | As a member, I should be required/able to fill in or update my personal information, events attended, projects/tasks/jobs completed, and the masterclasses/certificates held on my profile (so that LirtenHub can begin to recommend tasks/jobs to me that suit my profile). | 1 | Mikkawy | Bishoy | Mikkawy
4 | As a consultancy agency, I should be required/able to fill in or update my business information, partners, board members, and events organised (so that members can learn more about my agency). | 1 | Mikkawy | Bishoy | Mikkawy
5 | As a partner, I should be able to leave a review on a member’s profile after I’ve worked with them (so that future partners working with this member can see how they’ve done previously). | 3 | Shamel | Mariam | Ahmed Ashraf
6 | As a partner, I should be able to fill in or update my business information, partners, board members, events organised, and field of work (so that other users can view my information). | 1 | Bishoy | Shamel | Mariam
7 | As a partner, I should have my previous completed projects automatically listed on my profile (so that users can view older projects). | 3 | Mostafa | Ahmed Ashraf | Mariam
8 | As a member, I should be able to complete a form to give feedback on a partner that I’ve worked with before by visiting their profile (so that future members can see how they’ve done previously). | 2 | Mikkawy | Bishoy | Mostafa
9 | As a member, I should have masterclasses I’ve completed automatically listed on my profile (so that visitors of my page may view them). | 3 | Ahmed Ashraf | Shamel | Mariam
10 | As an admin, I should be able to review tasks submitted by partners (so that they can be available to view). | 3 | Shamel | Mariam | Ahmed Ashraf
11 | As an admin, I should be able to view member applications to a particular task (so that I can select an eligible member for the job). | 1 | Mariam | Ahmed Ashraf | Shamel
12 | As a member, I should be able to apply for a task if I’m eligible (so that I can be accepted or rejected for the job). | 1 | Mariam | Ahmed Ashraf | Shamel
13 | As an admin, I should be able to assign a consultancy to a task (so that they can begin to advise for the task). | 2 | Mostafa | Bishoy | Mikkawy
14 | As a member, I should be able to view recommendations for tasks that fit my skill set (so that it’s easier to find tasks for which I’m eligible). | 3 | Ahmed Ashraf | Shamel | Mariam
15 | As a member, I should receive a notification if my application is accepted (so that I can begin working on the task). | 1 | Bishoy | Mostafa | Mariam
16 | As an admin, I should be able to update a task’s current state (so that members and partners can see if it’s already in progress). | 1 | Mostafa | Bishoy | Mikkawy
17 | As a member, I should be able to request an assessment with an expert(so that they can guide me in choosing the right masterclass). | 3 | Ebram
18 | As a member, I should get notified when my request has been confirmed(so that I can arrange an assessment). | 2 | Bishoy | Shamel | Mostafa
19 | As a member, I should be able to view recommended masterclasses based on my assessment (so that I can apply for masterclasses). | 3 | Mikkawy | Bishoy | Mostafa
20 | As a member, I should be able to apply for masterclasses (so that I can begin working on them). | 1 | Mostafa | Shamel | Mikkawy