## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | MongoDB/Heroku
1.1 | Install and authenticate MongoDB/Heroku (so that we can use them in further implementation). | 2 | Mariam El-Shrif | Shamel Khalil | Ahmed Ashraf
1.2 | Implement MongoDB for models (so that they can use the database directly). | 1 | Shamel Khalil | Mariam El-Shrif | Ahmed Ashraf
1.3 | Implement MongoDB for CRUD (so that they insert and delete directly from the database). | 1 | Shamel Khalil | Mariam El-Shrif | Ahmed Ashraf
1.4 | Deploy website to Heroku (so that it can be accessed online). | 1 | Mariam El-Shrif | Shamel Khalil | Ahmed Ashraf
2 | Task Management
2.1 | As a partner, I should be able to submit a description of a task to be reviewed (so that it may be reviewed by an admin). | 1 | Shamel Khalil | Mariam El-Shrif | Mostafa
2.2 | As an admin, I should be able to review tasks submitted by partners (so that they can be available to view). | 1 | Shamel Khalil | Mariam El-Shrif | Mostafa
2.3 | As an admin, I should be able to view member applications to a particular task (so that I can select an eligible member for the job). | 1 | Mariam El-Shrif | Shamel Khalil | Mostafa
2.4 | As a member, I should be able to apply for a task if I’m eligible (so that I can be accepted or rejected for the job). | 1 | Mariam El-Shrif | Shamel Khalil | Mostafa
2.5 | As an admin, I should be able to assign a consultancy to a task (so that they can begin to advise for the task). | 2 | Mostafa | Bishoy | Mikkawy
2.6 | As a member, I should be able to view recommendations for tasks that fit my skill set (so that it’s easier to find tasks for which I’m eligible). | 5 | Ahmed Ashraf | Bishoy | Mikkawy
2.7 | As a member, I should receive a notification if my application is accepted (so that I can begin working on the task). | 2 | Bishoy | Mikkawy | Ebraam
2.8 | As an admin, I should be able to update a task’s current state (so that members and partners can see if it’s already in progress). | 1 | Mostafa | Mikkawy | Bishoy
3 | Roadmap
3.1 | As a member, I should be able to request an assessment with an expert(so that they can guide me in choosing the right masterclass). | 3 | Ebraam | Bishoy | Mikkawy
3.2 | As a member, I should get notified when my request has been confirmed(so that I can arrange an assessment). | 2 | Bishoy | Mikkawy | Ebraam
3.3 | As a member, I should be able to view recommended masterclasses based on my assessment (so that I can apply for masterclasses). | 5 | Mikkawy | Bishoy | Ahmed Ashraf
3.4 | As a member, I should be able to apply for masterclasses (so that I can begin working on them). | 1 | Mostafa | Bishoy | Ahmed Ashraf